## Sheet4
Row Labels | Count of Task Name | Row Labels | Average of %Completion
High | 3 | Marketing Campaign | 0.65
Low | 3 | Mobile App Testing | 0.575
Medium | 3 | Website Revamp | 0.5
Grand Total | 9 | Grand Total | 0.58333
Row Labels | Count of Task Name
Completed | 3
Not Started | 4
Work In Progress | 2
Grand Total | 9

## Project Data
Project Name | Task Name | Assigned To | Start Date | Due Date | Status | %Completion | Priority | Task Health
Website Revamp | Requirement Gathering | Alice | 2025-02-01 | 2025-02-05 | Work In Progress | 100% | High | On Track
Mobile App Testing | UI Design | Charlie | 2025-02-05 | 2025-02-25 | Work In Progress | 70% | Medium | On Track
Marketing Campaign | Frontend Development | Bob | 2025-02-13 | 2025-02-10 | Not Started | 45% | Low | Overdue
Website Revamp | Backend Integration | Diana | 2025-02-15 | 2025-02-28 | Completed | 0% | High | Done
Mobile App Testing | Test Case Writing | Ethan | 2025-02-03 | 2025-02-01 | Not Started | 100% | Medium | Overdue
Mobile App Testing | Functional Testing | Alice | 2025-02-08 | 2025-02-01 | Not Started | 60% | Low | Overdue
Mobile App Testing | Bug Fixing | Bob | 2025-02-15 | 2025-02-20 | Completed | 0% | High | Done
Marketing Campaign | Content Creation | Charlie | 2025-02-02 | 2025-02-01 | Not Started | 100% | Medium | Overdue
Marketing Campaign | Social Media Ads | Diana | 2025-02-07 | 2025-02-15 | Completed | 50% | Low | Done

## Dashboard
Metrics
TOTAL PROJECTS | 3
TOTAL TASKS | 9
% COMPLETED | 58.33%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Lists
Team Members | Status | Priority
Alice | Not Started | High
Bob | Work In Progress | Medium
Charlie | Completed | Low
Diana | Not Started | High
Ethan | Work In Progress | Medium
Alice | Completed | Low
Bob | Not Started | High
Charlie | Work In Progress | Medium
Diana | Completed | Low